## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/11/2025 - 9/25/2025
1 | 9/25/2025 - 10/17/2025 | We completed the database design and successfully deployed it to production on EC2. The frontend design for both the Events and Discover pages has been finalized, providing a clean and functional user interface. On the backend, we implemented the full architecture consisting of four layers—router, model, Docker containers, and database—ensuring a modular and maintainable structure. The security design has been completed, and all necessary tools have been configured and will be in use. Additionally, we set up backend services using FastAPI, created API models, and verified that both the Event router and User router are fully operational within the route layer. | 1. had some issues connecting backend services to the local database 2. ec2 instances for production db had some issues 3. endpoints for backend had some troubles 4. merge conflicts with readme files | 1. Some of the meetings were skipped because there wasnt any work that week. 2. demo had some issues which was fixed | We will continue working on Iteration 2, focusing on new features such as an interactive map and private events that allow users to host gatherings exclusively for themselves and their invited guests. Most technical issues have been resolved, so the next steps involve ongoing testing, issue fixing, and incremental improvements as new upgrades are implemented. | 50 | 20 | 10 | 5 | 5 | 230 | 219 | 11 | 29.5 | 17 | 45 | 44 | 18 | 22 | 14.5
2 | 10/17/2025 - 11/7/2025
3 | 11/7/2025 - 12/5/2025

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
Student Name | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General Communication and Management | Other Comments
Johannes Bekele
Saniya Bhambhvani
Javier Esteban de Celis
Vamsi Garghi
Yuanfei He
Shreya Rana

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Shreya
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 11/09-18/09 | 8 | 2 | approx 3 | 0 - Decided on the project idea 1 - created initial plan 2 - Working on our individual assigned roles 3 - Set up git | 2025-01-02 | 1 | approx 8 | 2025-01-02 | 0 | 0 | 0 | 0 | Use Chatgpt to research on some advanced High level requirements to get an idea | 1. Write sections of SPPP 2. Clone git, commit a message on git | None | N/A | 0 - Continue to define requirements 1 - Start implementation | 8
2 | 09/18 - 09/25 | 8 | 6 | 4 | 0 - Finished research on Functional Requirements that will be used 1 - Discussed and outlined the Project Scope/Functional Requirements 2 - Discussed Iteration and various requirements 6 - Researched on advanced feature | 8 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | Used Chatgpt to research on Event analytics | 1. Write sections of SPPP 2. Work on high level functional requirements | None | one | 0 - Work on implementation | 12
3 | 09/25 - 10/02 | 10 | 8 | 3 | 0 - Research on Security Design Plan and different tools that will be used 0 - Research on implementing security scanners 1 - Outline the Project Scope/Functional Requirements 3 - Release Iteration 0 | 10 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Used Chatgpt to research on various security scanners | 1. Created and worked on to implement Iteration 0 Release 2. Revised the Draft on the SPPP | None | None | 1 - Work on Lab 2 and SDD 2 - Review the PR's 3 - Implement Security scanners | 12
4 | 10/02 - 10/09 | 8 | 6 | 4 | 2 - Work on Security design 3 - Implement Security Scanners | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | Used Chatgpt to research on security design | 2- Gave commit and PR for Security Scanners | None | None
5 | 10/09 - 10/16 | 12 | 2 | 4 | 2 - Finish Security Design | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | Use Chatgpt to research on implementing endpoints | 1 - Worked on SDD and SPPP 2 - Review PR | None | None | 3 - Implement Attendees endpoints | 10

## Keni (Yuanfei)
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 9/11-9/17 | 5 | 2 | 3 | 0 – Decided on the project topic 1 – Setting up the project Git repository 2 – Divided tasks according to each team member’s role | 2025-02-03 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | 1 Set up git, commit a test message on git | NONE | N/A | N/A | 8
2 | 9/18-9/25 | 7 | 3 | 4 | 0 – participated in the group meeting 1 – contributed to the Quality Assurance Plan section 2 – dded images to the presentation slides. | 4 | 3 | 0.5 | [5 empty] | This week I participated in the group meeting, used ChatGPT to help draft and refine the content for the Quality Assurance Plan, and added images to the presentation slides. | 1. Write sections of SPPP 2. Work on Quality Assurance Plan |  |  |  | 8
3 | 9/25-10/2 | 6 | 3 | 3 | 0 – join the group meeting 1 – Writing std documentation | 3 | 6 | [6 empty] | use chat gpt to write userstory | 1. write section of std |  |  |  | 6
4 | 10/02 - 10/09 | 10 | 6 | 4 | 0-Studied testing technologies and learned automated testing tools (Jest/SuperTest). 4-Wrote part of the STD document related to automated testing. 5– Attended team meeting and discussed Iteration 1 progress. 6– Set up and configured backend test environment for future development. | 6 |  |  |  | 3 | 4 | 2 |  | I used ChatGPT to help structure the STD document, define test levels (unit, integration, system), and clarify coverage thresholds. I reviewed and adjusted the content before submitting.
5 | 10/09 - 10/16 | 11 | 7 | 4 | 3 - improved backend test cases, started implementing frontend test scripts 4 - verified API endpoints and frontend components through unit/integration tests 5 - attended team meeting and discussed test coverage goals 0 - learned additional Jest and React Testing Library usage | 3 |  |  | 4 | 2 | 2 |  |  | Used ChatGPT to review and optimize backend test cases, identify edge scenarios, and generate Jest/React Testing Library examples for frontend testing. Also used it to clarify CI pipeline setup and coverage report interpretation. The suggestions helped improve test organization and reduce debugging time. |  |  |  | 4- test frontdesk | 4

## Johannes
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/11 - 09/18 | 6 | 4 | 3 | 0 - learned git terminal commads and initializing using CLI, researched auth frameworks and learned mermaid commands for User diagrams 2 - Create User flow diagrams for authentication 6 - set up git | 2 |  | 1 |  |  |  | 1 |  | Used chatgpt to learn how to properly use mermaid syntax and help clean up the diagram i created | 1. Set up local git, commit a test message on git 2. Started to draft the project overview on my assigned work sections | 1. projects requirements and features not discussed 2. MVP features are not well defined | 1. Meet with team to discuss what we want for MVP features and what features we would want to implement | 1 - Start working on MVP 2 - discuss implementation and how to navigate PRs 3 - Create user flow diagrams for the different sections 4 - Work on management plan | 10
2 | 09/18 - 09/25 | 17 | 13 | 4 | 0 - Learned motion.dev graphics through tutorials 1 - Created documentation and define dockerfile information 2 - Started designing landing page 3 - Initialized Next.js application and created Dokcerfile 4 - Implement CI for github workflows for the frontend and defined guidelines for ESLint and prettier 5 - Reviewed PRs | 3 | 2 | 2 | 4 | 1.5 | 0.5 |  |  | Used chatgpt to learn how to properly use to debug and research framer motion animations Used cursor to implement front end CI and project structure from scratch | 1. Work on assigned secitons in the SPPP 2. Setup repo project structure 3. Participate in iteration 0 presentation 4. Review group memebers PR review 5. Create first PR for intialization feature | 1. Delay in PR's being reviewed. 2. Not enough reviewers for PRs | 1. Set up peer groups for reviews before hand | 0 - Decide on CD for the project 1 - Create a docker container for the postgeres db 2 - Create a docker compose to bundle backend, frontend and database 3 - Finish The landing page design 4 - Work on login page design | 13
3 | 09/25 - 10/02 | 6 | 3 | 3 | 1 - Created front-end Readme.md file to outline how to contribute to the frontend code 2 - Designed create events page with draft event preview 3 - Implement create-event page on route /create-event | 0.5 | 1 | 1.5 | 0 | 0 | 0 |  |  | Use Copilot to generate documentation for the fornt end read me | !. Reviewed PRs 2. Defined frontend structure of the application 3. Designed first set of pages for the project | No Issues this week | 1. Finish design page and fix auhtntication | 0 - Learn Clerk authentication through documentation 1- Define webhook requirements 2- Decide proteced vs public routes
4 | 10/02 - 10/09 | 12 | 8 | 4 | 1 - Outlined what routes are public and protected to see what pages a user can see when not authenticated 2 - Designed fake snub authnetication schema to test route protection 3 - Implemented snub authnetication | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 0 | Used ChatGPT and Cursor to deebug route protection issues and understand best practices for protected routes in Next.js. Aopilot assisted in generating mock authentication middleware | 1. Defined protected/public route structure 2. Tested route access control with mock users 3. Coordinated with backend to align authentication strategy | Encountered multiple routing comflicts when testing protected routes; needed additional middleware validation |  | 0 - Integrate Clerk webhook with frontend Signup 1 - Implement login redirection 3 - Begin work on protected dashboard route 4 - Conduct integration test for end-to-end signup flow | 10
5 | 10/09 - 10/16 | 15 | 11 | 4 | 0 - Went through Clerk documentation to understand implementation and safe practices 1 - Created documentatin on how Clerk is used for authenticating a user 2 - Create High level system design on how to handle webhooks recieved when new user is created 3 - Implemented Clerk auth and created custome webhook for when a new user is created to be sent to the database 4 - Tested webhook and designed HTTP status code to be sent back to Clerk client to communicate whether or not a user can be created 5 - Made Mermaid diagrams to show flow of the authentication 6 - Initalized Clerk SDK into the project | 2 | 2 | 1.5 | 5 | 2 | 1 | 1.5 | 0 | Used ChatGPT to troubleshoot Clerk webhooks and generate system design diagram in Mermaid syntax. Cursor and Copilot heloped generate the webhook handler and test HTTP responses | 1. Completed Clerk integration and user creation webhook 2. Updated documentation and Mermaid diagrams 3. Verified correct communication between Clerk and backend | Minor delay testing the webhook dur to signature verification error Also webhooks couldn't send to local dev enviroments so had to initialize ngrok for testing | Fixed by verifying Clerk secret and ensuring correct even type handling | 1 - Polish UI 2 - Connect backend API data to dashboard 3- Prepare documentation for iteration 1 submisison | 12

## Saniya
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date Range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/11 - 09/18 | 6 | 3 | 3 | 0 - Chose a project topic 1 - Discussed a basic project scope 6 - Git/GitHub setup, started research for configuration management plan | 1 | 1 |  |  |  |  | 1 |  | Used ChatGPT to give examples of the structure of configuration management plans | 1. Set up Git, commit a test message (introduction) 2. Completed Lab 1 3. Helped with basic scope of project with Shreya and Sai 4. Research on Configuration Management Plan | 1. SSH on Git | 1. Figured out SSH setup and finished Git/GitHub setup | 0 - Continue to research Configuration Management Plan 1 - Solidfy project scope 2 - Compose an initial draft of the Configuration Management Plan, work on Iteration 0 presentation 6 - Organize branch structure in GitHub | 8
2 | 09/18 - 09/25 | 8 | 4 | 4 | 0 - Finish research on Configuration Management Plan and different tools that will be used 1 - Discuss and outline the Project Scope/Functional Requirements 2 - Create the Iteration #0 Presentation and Configuration Management Plan 6 - Research branch structure for Git/GitHub | 0.5 | 0.5 | 2 |  |  |  | 1 |  | Used ChatGPT to give a list of SAST/DAST tools to use that are compatible with our team's tech stack. | 1. Finished my Initial Draft on the Configuration Management Plan 2. Created, worked on, and finished Iteration #0 Presentation 3. Revised and finished the Final Draft on the SPPP | N/A | N/A | 0 - Research on SAST/DAST and CI/CD tools 2 - Start working on the frontend and database 6 - Continue organizing the branch structure in GitHub | 10
3 | 09/25 - 10/02 | 6 | 3 | 3 | 2 - Work on database 5 - Review PRs |  |  | 1 |  |  | 2 |  |  | N/A | 1. Reviewed PRs 2. Worked on database 3. Finished Quiz #1 | N/A | N/A | 1 - Work on Lab 2 and SDD 2 - Design the Discover Page 5 - Review PRs | 8
4 | 10/02 - 10/09 | 7 | 3 | 4 | 0 - Learn about Next.js and Tailwind CSS 5 - Review PRs | 1 |  |  |  |  | 2 |  |  | N/A | 1. Finished Lab 2 2. Worked on SDD 3. Created Discover Page on frontend 4. Reviewed PRs | N/A | N/A | 1 - Revise the SPPP and work on SDD 2 - Create the Iteration #1 Presentation and design the Discover Page 5 - Review PRs | 10
5 | 10/09 - 10/16 | 10 | 7 | 3 | 1 - Revise the SPPP and work on the SDD 2 - Create Iteration 1 Presentation and design Discover Page UI |  | 4 | 3 | [5 empty] | N/A | 1. Finished revising SPPP 2. Worked on and finished SDD 3. Created, worked on, and finished Iteration #1 Presentation 4. Created Discover Page UI Design | N/A | N/A | 3 - Work on connection between the frontend and backend on EC2 | 12

## Javier
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/11 - 09/18 | 6 | 3 | 3 | 5 - lead meetings, create agendas, ... 5 - make project plan, send reminders to team members 6 - create git repo | [5 empty] | 2 | 1 |  | Used warp ai terminal when creating the repo to have some help. Other than that used chatgpt to start coming up with the project overview and related work sections for iteration 0 | 1. Set up git, commit a test message on git 2. Started to draft the project overview and related work sections | 1. project idea is too broad 2. MVP features are not well defined | 1. working on reducing the scope and aligning on project idea goal and mvp must have features | 1 - help define the high level requirements 2- start with an initial draft design 7 - worki on project iteratio 0 deliverables 6 - help decide tools and tech stack that the team will use | 10
2 | 09/18 - 09/25 | 14 | 10 | 4 | 5 - lead meetings, create agendas, ... 5 - make project plan, send reminders to team members 6 - setup repo structure 6 - setup backend overall structure and ci | [5 empty] | 5 | 9 |  | Used cursor to help setup the repo from scratch. Used copilot in the repo to make it so that it reviews every pr a team member creates. Used chatgpt for help with the overview and related work sections | 1. Write to sections for the SPPP 2. Review every section in the SPPP and provide feedback 3. Review presentation for iteration 0 4. Setup repo structure 5. Setup backend structure and ci with python, ruff, pytest, uv, and tox | 1. coordinating the team to have all deliverables in time for project iteration 0 | 1. better difne roles and tasks for every member in the team | 2- help finishing the desing of the database 2- design the backend enpoints needed for the mvp 2- desing the sql interaction done by the backend 3- implement the backend endpoints needed for the mvp 6- help any left over configuration that is needed in the repo | 15
3 | 09/25 - 10/02 | 18 | 15 | 3 | 2 - start project design 2 - go over sdd and std to assign sections to the right team members to leverage their skills and interests 3 - draft implementation of REST API endpoints 5 - lead meetings, create agendas, ... |  |  | 5 | 8 |  | 2 |  |  | Used copilot in the repo to make it so that it reviews every pr a team member creates. | 1. Read sdd and std docs 2. Divide setcions and assign them to team members 3. Start to populate sdd based on the project design | 1. get team members to start working early so that iteration 1 is smoother than iteration 0 | 1. divide and assign tasks early on for all team members | 2 - continue with the project design with a focus on the database and backend design 3 - implement initial database configuration to connect the backend to the postgressql database 3 - implement the models and endpoint routes to provide swagger docs for the entire team 3 - improve database design to fit the backend workflow 5 - lead meetings, create agendas, ... 5 - go over iteration 1 deliverables and plan week ahead by assigning all tasks to team members and provide deadlines 6 - setup postgressql database docker compose file and workflow | 25
4 | 10/02 - 10/09 | 24 | 20 | 4 | 2 - continue with the project design with a focus on the database and backend design 3 - implement initial database configuration to connect the backend to the postgressql database 3 - implement the models and endpoint routes to provide swagger docs for the entire team 3 - improve database design to fit the backend workflow 5 - lead meetings, create agendas, ... 5 - go over iteration 1 deliverables and plan week ahead by assigning all tasks to team members and provide deadlines 6 - setup postgressql database docker compose file and workflow |  |  | 7 | 7 |  | 3 | 3 |  | Used copilot in the repo to make it so that it reviews every pr a team member creates. Used copilot to understand docker volumes and finalize the docker compose file. Used copilot to improve the database design Used copilot to debug issues with endpoint routes and fastapi | 1. Conitnue to complete several sections of the sdd document | 1. get team members to start working early so that iteration 1 is smoother than iteration 0 | 1. divide and assign tasks early on for all team members | 2 - review sppp based on professor feedback and improve plan and proposal 2 - finish remaining sections assigned to me of the sdd 2 - create diagrams for the overall and backend architecture based on the design done for the overall project 2 - review sdd and std to provide feedback and complete the final version of both docs 3 - update and improve overall repo readme 3 - implement the functionality and tests for the users set of endpoint from the service layer to the database layer 5 - lead meetings, create agendas, ... 5 - help team members complete individual progress reports 5 - assure consistency between individual progress reports 5 - complete team progress report for iteration 1 6 - help configuring the database deployment in production 6 - help configuring the frontend and backend deployment in production | 25
5 | 10/09 - 10/16 | 24 | 20 | 4 | 2 - review sppp based on professor feedback and improve plan and proposal 2 - finish remaining sections assigned to me of the sdd 2 - create diagrams for the overall and backend architecture based on the design done for the overall project 2 - review sdd and std to provide feedback and complete the final version of both docs 3 - update and improve overall repo readme 3 - implement the functionality and tests for the users set of endpoint from the service layer to the database layer 5 - lead meetings, create agendas, ... 5 - help team members complete individual progress reports 5 - assure consistency between individual progress reports 5 - complete team progress report for iteration 1 6 - help configuring the database deployment in production 6 - help configuring the frontend and backend deployment in production |  |  | 5 | 7 |  | 3 | 5 |  | Used copilot in the repo to make it so that it reviews every pr a team member creates. Used copilot to help me imporve the initial SPPP based on the prof feedback Used copilot to help implement the users endpoints as well as the end to end testing | 1. Conitnue to complete several sections of the sdd document 2. improve sppp based on feedback | 1. coordinate all iteration 1 deliverables while leading the backend design and implementation | 1. delegate the implementation of a major part of the backend to other team members | 2 - help design the new features to be added after the MVP is completed 3 - implement the new features based on the design agreed on with the team 5 - continue to lead meeting, create agenda, ... 6 - continue to help with the cd for the frontend and backend | 20

## Vamsi
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/11 - 09/18 | 6 | 3 | 3 | Individual Task Breakdown 0 - learning - github setup 1 - requirement analysis - project name/planning 5 - created jira board, created meetings 6 - configuration git environemnt and lab | 1 | 1 |  |  |  | 4 | 2 |  | Used chatgpt to solve remote access isues with git. I was able to get remote origin acces done correctly, and the commands were listed from it | 1. create jira board and dailystandup meetings for project updates 2.git has been set up and my lab1 update were pushed correctly 3. prepare planning for the project and the other planning | 1. github setup | 1. github issue was fixed | 2. coming up with proejct planing and jira features/stories/tasks for each person from it | 5
2 | 09/19 - 09/25 | 8 | 4 | 4 | Individual Task Breakdown 0 - learning what docker containers and other deployment tools are 1 - requirement analysis 2 - design the schema and had an ERD 5 - created and managed many meetings and other aspects | 0.5 | 1 | 2 |  |  | 0.5 |  |  | Used chatgpt to get naming convention for columns names | 1. created database tables and columns 2. created ERD diagram of those and the relationships it has. 3. created lots of meetings and updated the meetings minutes for docs and other document. 4. worked on presentation for the first iteration and created a bunch of PPT slides for functionality work | 1. db schema work | 1. schema is working now and ERD was completed as well | 1. starting work on project. 2. implementing the db into the main git branch and have it reviewed | 8
3 | 09/25 - 10/02 | 13 | 10 | 3 | Individual Task Breakdown 0 - learning - aws ec2 instance launch 1 - requirement analysis - user stories 2 - design - designed db 3 - implementation - implemented db on local system 5 - communication/management - set up meetings and contributed to meeting minutes | 1 | 2 | 6 |  |  | 1 |  |  | used chatgpt to learn about aws ec2 instances and the best configuration for them | 1. set up user stories for all 2. designed and modified db design and column name and datatypes 3. implement db on local system and got the tables working correctly 4. set up daily standup and worked on meeting minutes | 1. user stories not up to standard 2. db working on local but need to get it into the cloud for others | 1. user stories fixed 2. db need to be implemented into ec2 instance | 1. getting db into docker and into ec2 | 15
4 | 10/02 - 10/09 | 19 | 15 | 4 | Individual Task Breakdown 0 - learning - docker containers and how to use them 1 - requirement analysis - db requirments and frontend requirments 4 - test - db changes and db upgrades 5 - communication/management - meeting minutes, daily standup 6 - configuration/environment - configured docker environemnt | 2 | 3 |  | 4 | 6 |  |  |  | used chatgpt to learn about docker containers and also modify db requirments based on best practies. tested db changes using sql statements generated by chgatgpt | 1. write up sections of SDD for database design 2. SPPP AI usage logs 3. deploy database on EC2 4. set up meeting and did meeting minutes 5. configured docker environment | 1. SDD not completed due to DB changes 2. chatgpt links not working | 1. SDD completed and deisgn ready | 1. deploy db and getting front end and backend set up | 15
5 | 10/09 - 10/16 | 19 | 15 | 4 | Individual Task Breakdown 1 - requirement analysis - what requirments needed to host db on EC2 2 - design - designed ec2 docker container and yaml file 3 - implementation - implemented db in ec2 4 - test - tested db in ec2 5 - communication/management - daily standup and meeting minutes 6 - configuration/environment - configured cloud environment for db and frontend backend |  | 1 | 4 | 4 | 4 | 1 | 1 |  | used chatgpt to get into ec2 instance, get docker working on ec2, and delpoyed the db and frontend and backend containers | 1. deploy db in ec2 2. deploy frontend and backend on ec2 3. set up docker in ec2 4. work on SPPP 5. work on SDDD db design 6. set up user stories | 1. ec2 instance on my school was not working correctly and did not work after a while 2. docker container had some issues 3. db tables had some issues with datatypes | 1. ec2 instance was launched in personal and working fine 2. docker container working correctly 3. db tables working correctly | 1. working on backend for the website and the demo 2. working on connectiing the frontend and backend on ec2 | 20