## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/11/2025 - 09/25/2025
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Shreya
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 11/09-18/09 | 8 | 2 | approx 3 | 0 - Decided on the project idea 1 - created initial plan 2 - Working on our individual assigned roles 3 - Set up git | 2025-01-02 | 1 | approx 8 | 2025-01-02 | 0 | 0 | 0 | 0 | Use Chatgpt to research on some advanced High level requirements to get an idea | 1. Write sections of SPPP 2. Clone git, commit a message on git | None | N/A | 0 - Continue to define requirements 1 - Start implementation | 8
2 | 09/18 - 09/25 | 8 | 6 | 4 | 0 - Finished research on Functional Requirements that will be used 1 - Discussed and outlined the Project Scope/Functional Requirements 2 - Discussed Iteration and various requirements 6 - Researched on advanced feature | 8 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | Used Chatgpt to research on Event analytics | 1. Write sections of SPPP 2. Work on high level functional requirements | None | one | 0 - Work on implementation | 12

## Keni (Yuanfei)
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
2 | 11/09-18/09 | 8 | 2 | 2 | 0 – Decided on the project topic 1 – Setting up the project Git repository 2 – Divided tasks according to each team member’s role | 2025-02-03 | 1 |  | 0 | 0 | 0 | 0 | 0 |  | N/A | NONE | N/A | N/A | 8

## Saniya
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date Range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/11 - 09/17 | 6 | 3 | 3 | 0 - Chose a project topic 1 - Discussed a basic project scope 6 - Git/GitHub setup, started research for configuration management plan | 1 | 1 |  |  |  |  | 1 |  | Used ChatGPT to give examples of the structure of configuration management plans | 1. Set up Git, commit a test message (introduction) 2. Completed Lab 1 3. Helped with basic scope of project with Shreya and Sai 4. Research on Configuration Management Plan | 1. SSH on Git | 1. Figured out SSH setup and finished Git/GitHub setup | 0 - Continue to research Configuration Management Plan 1 - Solidfy project scope 2 - Compose an initial draft of the Configuration Management Plan, work on Iteration 0 presentation 6 - Organize branch structure in GitHub | 8
2 | 09/18 - 09/25 | 8 | 4 | 4 | 0 - Finished research on Configuration Management Plan and different tools that will be used 1 - Discussed and outlined the Project Scope/Functional Requirements 2 - Created the Iteration #0 Presentation and Configuration Management Plan 6 - Researched branch structure for Git/GitHub | 0.5 | 0.5 | 2 |  |  |  | 1 |  | Used ChatGPT to give a list of SAST/DAST tools to use that are compatible with our team's tech stack. | 1. Finished my Initial Draft on the Configuration Management Plan 2. Created, worked on, and finished Iteration #0 Presentation 4. Revised and finished the Final Draft on the SPPP | N/A | N/A | 0 - Research on SAST/DAST and CI/CD tools 2 - Start working on the frontend and database 6 - Continue organizing the branch structure in GitHub | 10

## Johannes
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/11 - 09/18 | 6 | 4 | 3 | 0 - learned git terminal commads and initializing using CLI, researched auth frameworks and learned mermaid commands for User diagrams 2 - Create User flow diagrams for authentication 6 - set up git | 2 |  | 1 |  |  |  | 1 |  | Used chatgpt to learn how to properly use mermaid syntax and help clean up the diagram i created | 1. Set up local git, commit a test message on git 2. Started to draft the project overview on my assigned work sections | 1. projects requirements and features not discussed 2. MVP features are not well defined | 1. Meet with team to discuss what we want for MVP features and what features we would want to implement | 1 - Start working on MVP 2 - discuss implementation and how to navigate PRs 3 - Create user flow diagrams for the different sections 4 - Work on management plan | 10
1 | 09/18 - 09/25 | 17 | 13 | 4 | 0 - Learned motion.dev graphics through tutorials 1 - Created documentation and define dockerfile information 2 - Started designing landing page 3 - Initialized Next.js application and created Dokcerfile 4 - Implement CI for github workflows for the frontend and defined guidelines for ESLint and prettier 5 - Reviewed PRs | 3 | 2 | 2 | 4 | 1.5 | 0.5 |  |  | Used chatgpt to learn how to properly use to debug and research framer motion animations Used cursor to implement front end CI and project structure from scratch | 1. Work on assigned secitons in the SPPP 2. Setup repo project structure 3. Participate in iteration 0 presentation 4. Review group memebers PR review 5. Create first PR for intialization feature | 1. Delay in PR's being reviewed. 2. Not enough reviewers for PRs | 1. Set up peer groups for reviews before hand | 0 - Decide on CD for the project 1 - Create a docker container for the postgeres db 2 - Create a docker compose to bundle backend, frontend and database 3 - Finish The landing page design 4 - Work on login page design | 13

## Javier
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/11 - 09/18 | 6 | 3 | 3 | 5 - lead meetings, create agendas, ... 5 - make project plan, send reminders to team members 6 - create git repo | [5 empty] | 2 | 1 |  | Used warp ai terminal when creating the repo to have some help. Other than that used chatgpt to start coming up with the project overview and related work sections for iteration 0 | 1. Set up git, commit a test message on git 2. Started to draft the project overview and related work sections | 1. project idea is too broad 2. MVP features are not well defined | 1. working on reducing the scope and aligning on project idea goal and mvp must have features | 1 - help define the high level requirements 2- start with an initial draft design 7 - worki on project iteratio 0 deliverables 6 - help decide tools and tech stack that the team will use | 10
2 | 09/19 - 09/25 | 14 | 10 | 4 | 5 - lead meetings, create agendas, ... 5 - make project plan, send reminders to team members 6 - setup repo structure 6 - setup backend overall structure and ci | [5 empty] | 5 | 9 |  | Used cursor to help setup the repo from scratch. Used copilot in the repo to make it so that it reviews every pr a team member creates. Used chatgpt for help with the overview and related work sections | 1. Write to sections for the SPPP 2. Review every section in the SPPP and provide feedback 3. Review presentation for iteration 0 4. Setup repo structure 5. Setup backend structure and ci with python, ruff, pytest, uv, and tox | 1. coordinating the team to have all deliverables in time for project iteration 0 | 1. better difne roles and tasks for every member in the team | 2- help finishing the desing of the database 2- design the backend enpoints needed for the mvp 2- desing the sql interaction done by the backend 3- implement the backend endpoints needed for the mvp 6- help any left over configuration that is needed in the repo | 15

## Vamsi
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/11 - 09/18 | 6 | 3 | 3 | Individual Task Breakdown 0 - learning - github setup 1 - requirement analysis - project name/planning 5 - created jira board, created meetings 6 - configuration git environemnt and lab | 1 | 1 |  |  |  | 4 | 2 |  | Used chatgpt to solve remote access isues with git. I was able to get remote origin acces done correctly, and the commands were listed from it | 1. create jira board and dailystandup meetings for project updates 2.git has been set up and my lab1 update were pushed correctly 3. prepare planning for the project and the other planning | 1. github setup | 1. github issue was fixed | 2. coming up with proejct planing and jira features/stories/tasks for each person from it | 5
2 | 09/19 - 09/25 | 8 | 4 | 4 | Individual Task Breakdown 0 - learning what docker containers and other deployment tools are 1 - requirement analysis 2 - design the schema and had an ERD 5 - created and managed many meetings and other aspects | 0.5 | 1 | 2 |  |  | 0.5 |  |  | Used chatgpt to get naming convention for columns names | 1. created database tables and columns 2. created ERD diagram of those and the relationships it has. 3. created lots of meetings and updated the meetings minutes for docs and other document. 4. worked on presentation for the first iteration and created a bunch of PPT slides for functionality work | 1. db schema work | 1. schema is working now and ERD was completed as well | 1. starting work on project. 2. implementing the db into the main git branch and have it reviewed | 8