## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| Lack of motivation or responsibility | Individuals in the team may lose focus or fail to complete assigned tasks | 3 | 3 | 3 | 27 | Team Leader and all members | 2025-09-30 | Regular check-ins through daily standups, distributed workloads fairly, introduce peer accountability | Dail meetings have maintained motivation | Open
Communication | duplicate work | Team member may unknowingly work on the same component | 3 | 2 | 3 | 18 | Team leader |  | Maintain a shared task board (JIRA) | No duplication so far | Open
| worked on wrong components | Miscommunication may cause someone to work on a. low-priority or wrong task | 2 | 4 | 3 | 24 | Assigned developer + reviewer |  | Clarify tasks with acceptance criteria |  | Open
Requirements | unclear requirements | Ambigious speicification | 3 | 1 | 3 | 36 | Design and implementation leader |  | Document requirements, confirm with rest of the team | Requirements clarified through meetings | Open
| scope creep | Uncrontrolled feature expansion | 4 | 5 | 4 | 90 | Team leader |  | Enforce scope freeze after requirement approval | No scope creep so far | Open
| constant requirements changes | Frequent updates acuse rework and stalling | 3 | 4 | 4 | 48 | Requirement leader |  | Change control process with approval required | Minor changes managed with approval | Open
Management | improper planning | Poor scheduling leads to misse deadlines | 3 | 4 | 3 | 36 | Team leader |  | Use project timeline with milestones | Adjustments made to maintain progress | Open
Technology competence | Not familiar with the framework used | Steep learning curve delays development | 3 | 4 | 3 | 36 | All devs |  | Provide tutoials, and clear guidlines. Possible pair programming | Framework basics learned | Open
| Not familiar with the programming language used | Error due to lack of experience | 3 | 3 | 3 | 27 | Developers |  | Practice excercises, code reviews | Skills improving | Open
| Not familiar with unit testing | Lack of test coverage introduces bugs | 4 | 4 | 3 | 48 | QA leader |  | Training on Jest, require testts for PRs | Coverage improving | Open
| Other technology incompetence | Issues with tools like Docker, CI/CD | 2 | 3 | 3 | 18 | Configuration Leader |  | Document worflows, practice setups | Initial hiccups resolved | Open
| Not familiar with Git | Merge conflicts and lost work | 3 | 4 | 2 | 24 | All members |  | Git worflow | Git usage improved | Open
Design and implementation | improper technology stack | Poor system architecture creates rework | 3 | 5 | 4 | 60 | Requirement leader + Design and Implementation leader |  | Validate tech stack before commitment | Stack finalized | Open
| Messy code | Hard-to-maintain code | 3 | 3 | 2 | 18 | All devs |  | Enfore linting, PR reviews | Style guides applied | Open
Testing | Not enough testing | Insufficient converage increases defects | 4 | 5 | 4 | 80 | QA leader |  | Write automated tests for all modules | Unit tests in progress | Open
Integration and deployment | Not enough time for integration and deployment | Final release may fall if integration delays | 3 | 5 | 4 | 60 | Configuration Leader + Security Leader |  | Continuous integration, regular deployments | Firest deployment succesful | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.